## Slide 1: Civil-Military cooperation EANS and Ämari Airbase
Üllar Salumäe
13.november 2015

## Slide 2: Introduction and background
SINGLE EUROPEAN SKY
The State shall ensure safe and efficient air navigation service (incl. Air traffic control services) provision, which is in line with the airspace organisation and its use as laid down in Regulation (EC) No 551/2004 of the European Parliament and of the Council of 10 March 2004 on the organisation and use of the airspace in the single European sky (Airspace Regulation).
BACKGROUND
Between 2008-2012 a new ground infrastructure, the Air Base security facilities as well as the following preparations were done for Ämari:
  up-to-date infrastructure required for the functionality of the Air Base,
  majority of the technical support for the Air Base operations: vehicle fleet, aerodrome maintenance facilities and equipment and many more,
  modern radio and navigation aids,
  high-skilled personnel trained for working with the modern infrastructure and technical equipment.
(air traffic control) services at full range were not developed. at that time.
Every year the air traffic flows to Ämari have been growing and the trend is still on upturn (incl training exercises).
When there are two aerodromes close to each other it is not reasonable (nor possible) to establish two separate airspaces for the provision of approach control services.

## Slide 3
Statistics of landings Ämari Air Base
2011
2012
2013
2014
10.2015
685
891
1140
1776
1525

## Slide 4: Project objectives and benefits for future
OBJECTIVES
Development of approach control procedures and service for Ämari aerodrome.
As an outcome of the project a portion of controlled airspace around Ämari aerodrome (Control Zone) was established, Tallinn TMA was expanded in order to ensure safe manoeuvres for departing and arriving aircraft till their reaching en-route phase/landing.
In parallel we implemented 3NM lateral separation minima within Tallinn TMA
BENEFITS FOR FUTURE
The activities within the project framework during two years helped improve:
  the enhanced civil-military cooperation,
  Efficient use of Estonian airspace, and incorporated traffic from Ämari aerodrome to the overall flight operations. operations.

## Slide 5: Roadmap and activities results
Kick off
EETN TMA
3.2014
Expansion of Tallinn TMA and (establishment of Ämari CTR).
Development of a common airspace concept of Ämari CTR and Tallinn TMA.
Procedures
10.2014
Development of air traffic control procedures for Ämari and
updating ATS Procedures Manual
3.2015
Training of Tallinn air traffic controllers (including theoretical and Simulator training).
CNS/ATM
2.2015
Needs assessment and procurement of communication, navigation and surveillance systems as required for the cooperation Air Base ↔ EANS.
Configuration of new APP position.
Legal issues
10.2013
AIP and charts
4.2015
Contracts.
Development of the service package for Approach Control service at Ämari aerodrome.
Implementation
12.2014
AIP changes, instrument flight procedure design, charts
Safety
4.2015
Establishment of Ämari approach control service and implementation of the respective technical support at Tallinn air traffic control centre
Post implementation monitoring
2013-2015
8 contributory risk assessments (equipment, procedures and meteo).
The safety assessment was reviewed periodically alongside with the project and 3 up to date versions where published.
30.04-30.08.2015
Implementation of 3NM separation minima and enabling use of ARR/DIR working configuration for reducing workload and increase the capacity at APP position has been successful and safe - the best proof of it is absence of flight occurrences relating to it.
Training

## Slide 6: Meantime some facts and numbers
Approx.
15 000
man-hours
All EANS departments were involved in the project:
19 months active preparation time
Development:
Project management
Basics for statistics and invoicing
Finance:
Service pricelist
CNS/ATM:
New APP position for Ämari
Technical preparations
Lawyers:
Preparation of contracts
Safety:
Safety assessment of the project
AIS and charts:
AIP changes, instrument flight procedure design, charts
ATM: EETN TMA,
Air traffic control procedures,
Training of air traffic controllers,
Development of new APP position,
Legal issues,
AIP changes and charts,
Safety,
Implementation, post- implementation monitoring
35 employees involved
(+ all ATCO`s)

## Slide 7: Implementation and post implementation monitoring
Implementation
The implementation took place on 30.04.2015 at 00.01 UTC and covered all the following aspects:
Check/verification of the new APP position configuration
Check of the systems software functionality
Procedures and related documentation
Training and personnel licensing.
Post implementation monitoring
During the observation period no inconsistencies in the air traffic control process
Implementation of 3NM separation minima and the use of ARR/DIR working configuration for reducing workload at APP positions has been successful and safe - the best proof of it is absence of flight occurrences relating to it.

## Slide 8: 3 important things to remember!
Believe in yourself and in your people and what seems impossible now, that will be possible when together in a team of co-thinkers!
We have had some time off and now are ready for new projects. Interested? Who would like to challenge participation in the development of approach control procedures?
COMMUNICATION !
The base of cooperation

## Slide 9
Colonel Jaak Tarien
Commander of Estonian Air Force
Estonia has a reputation of a “little country that can (get things done)”. This project, and our overall flexible airspace management, show that we live up to this reputation. Through excellent cooperation between the EANS and AF we have managed to achieve the optimal use of our very compact airspace so that both defence and civilian needs are met. Thank you!
Tanel Rautits
Chairman of EANS Management Board/ CEO
It is an excellent project, which has given our and military specialists a possibility to create something new and to do it in such a demanding environment where both civil and military experts could work together as a team. Credit must be given to all the participants. Great job!

## Slide 10
Reet Stamm
Project Manager of Ämari
Lieutenant/ Air Force
The Air Force would like to express their gratitude to the Ministry of Economic Affairs and Communications, EANS, Estonian CAA and EAVA for the cooperation. We highly appreciate the enthusiasm, professional contribution and competence of your staff who helped the project success.
Liivi Kumari
Project Coordinator of Ämari
Project Manager EANS
Apart from the professional and cooperation lessons I think during the course of the project we all have learnt to better understand each other.
Now it is no longer scary for our team members to jump into water at a unknown place.
A supporting team has sufficient strength and motivation for the coming challenges. Thank you!

## Slide 11: Thank you!
Questions!
www.eans.ee
www.lennujuht.ee
ullar@eans.ee